## Project Plan
Task | Start Week | End Week | Duration (Weeks) | Dependencies | Start Date | End Date
Planning & Permits | 0 | 2 | 2 |  | 2026-03-02 | 2026-03-16
Demolition | 2 | 3 | 1 | Planning & Permits | 2026-03-16 | 2026-03-23
Framing | 3 | 5 | 2 | Demolition | 2026-03-23 | 2026-04-06
Electrical Rough-In | 5 | 7 | 2 | Framing | 2026-04-06 | 2026-04-20
Plumbing Rough-In | 5 | 7 | 2 | Framing | 2026-04-06 | 2026-04-20
Rough Inspections | 7 | 8 | 1 | Electrical & Plumbing Rough-In | 2026-04-20 | 2026-04-27
Insulation & Drywall | 8 | 10 | 2 | Rough Inspections | 2026-04-27 | 2026-05-11
Exterior Vinyl Siding & Paint | 8 | 12 | 4 | Framing | 2026-04-27 | 2026-05-25
Paint & Doors | 10 | 11 | 1 | Drywall | 2026-05-11 | 2026-05-18
Flooring | 11 | 12 | 1 | Paint | 2026-05-18 | 2026-05-25
Kitchen Install | 12 | 13 | 1 | Flooring | 2026-05-25 | 2026-06-01
Bathroom Finishes | 12 | 14 | 2 | Drywall & Flooring | 2026-05-25 | 2026-06-08
Final Electrical | 14 | 15 | 1 | Fixtures Installed | 2026-06-08 | 2026-06-15
Final Plumbing | 14 | 15 | 1 | Fixtures Installed | 2026-06-08 | 2026-06-15
Final Inspections | 15 | 16 | 1 | Final Electrical & Plumbing | 2026-06-15 | 2026-06-22